## Proj info
Proj_name | Proj_Manager | Proj start date | Proj end date | Proj Type
x | A | 2021-12-01 | 2022-12-15 | Android App
y | B | 2021-12-30 | 2022-01-20 | Web App
z | B | 2021-11-20 | 2021-12-30 | BI Dashboards

## Tasks
Proj_name | Date | Task name | Task status
x | 2021-12-01 | Requirement Gathering | Completed
x | 2021-12-04 | Design specification | Pending
x | 2021-12-07 | Implementation | Pending
x | 2021-12-13 | Verification | Pending
x | 2021-12-15 | Maintenance | Pending
y | 2021-12-30 | Requirement Gathering | Completed
y | 2022-01-04 | Design specification | Ongoing
y | 2022-01-09 | Implementation | Pending
y | 2022-01-18 | Verification | Pending
y | 2021-12-20 | Maintenance | Pending
z | 2021-11-20 | Requirement Gathering | Completed
z | 2021-11-29 | Design specification | Ongoing
z | 2021-11-04 | Implementation | Ongoing
z | 2021-11-20 | Verification | Ongoing
z | 2021-12-30 | Maintenance | Pending

## KPIs
Proj name | Date | cost | selling price | profit
x | 2021-12-01 | 10000 | 12000 | 2000
x | 2021-12-04 | 2000 | 4000 | 2000
x | 2021-12-07 | 1390 | 6666 | 5276
x | 2021-12-13 | 2421 | 4433 | 2012
x | 2021-12-15 | 4322 | 6544 | 2222
y | 2021-12-30 | 3989 | 9121 | 5132
y | 2022-01-04 | 2080 | 8324 | 6244
y | 2022-01-09 | 2188 | 9212 | 7024
y | 2022-01-18 | 1999 | 8121 | 6122
y | 2021-12-20 | 3333 | 7111 | 3778
z | 2021-11-20 | 1222 | 9111 | 7889
z | 2021-11-29 | 2222 | 8111 | 5889
z | 2021-11-04 | 4886 | 1777 | -3109
z | 2021-11-20 | 2788 | 11331 | 8543
z | 2021-12-30 | 2888 | 4666 | 1778